## Sheet1
REQUIREMENT TRACIBILITY MATRIX
Project Name | Lambdatest Project
Project ID | 1
Project Manager | Sanket Sarode
Sr.No. | Req. ID | TC_ID | Test case description | Test Result | Defect ID | Defect Status
1 | REQ_001 | TC_001 | Verify that user is unable to register with invalid email ID. | Fail | DEF_001 | In Progress
2 | REQ_002 | TC_002 | Verify that user is unable to register with invalid name. | Fail | DEF_002 | In Progress
3 | REQ_003 | TC_003 | Verify that user is unable to register with invalid First name. | Fail | DEF_003 | In Progress
4 | REQ_004 | TC_004 | Verify that user is unable to register with invalid Telephone details. | Fail | DEF_004 | In Progress
5 | REQ_005 | TC_005 | Verify that user is unable to register with valid details. | Pass | NA | NA
6 | REQ_006 | TC_006 | Verify that user is unable to register with all invalid details. | Fail | DEF_005 | In Progress
7 | REQ_007 | TC_007 | Verify that whether user is able to login using valid email Id and password. | Pass | NA | NA
8 | REQ_008 | TC_008 | Verify that whether user is able to login using invalid email Id and valid password. | Pass | NA | NA
9 | REQ_009 | TC_009 | Verify that whether user is able to login using valid email Id and invalid password. | Pass | NA | NA
10 | REQ_010 | TC_010 | Verify that whether user is able to login using invalid email Id and invalid password. | Pass | NA | NA
11 | REQ_011 | TC_011 | Verify that whether user is able to login using empty email Id and password. | Pass | NA | NA
12 | REQ_012 | TC_012 | Verify that whether user is able to login using empty email ID field. | Pass | NA | NA
13 | REQ_013 | TC_013 | Verify that whether user is able to login using empty password field. | Pass | NA | NA
14 | REQ_014 | TC_014 | Verify that whether user is able to see search bar on the home page. | Pass | NA | NA
15 | REQ_015 | TC_015 | Verify that whether user is unable to click the search option without entering any thing in search bar field. | Fail | DEF_006 | In Progress
16 | REQ_016 | TC_016 | Verify that whether user is able to see all the products related to iphone only,when user enters I phone in search bar. | Fail | DEF_007 | Not started
17 | REQ_017 | TC_017 | Verify that user is unable to see any kind of search results unless and untill user provides any search. And user should get pop up message like please enter in ssearch field. | Fail | DEF_008 | Not started
18 | REQ_018 | TC_018 | Verify that whether user is able to see iMac product, but not that product should not be repetative. | Fail | DEF_009 | Not started
19 | REQ_019 | TC_019 | verify that whether user is able to see all the products related to iMac when user searches iMacc in search bar. | Fail | DEF_010 | Not started
20 | REQ_020 | TC_020 | Verify that whether user is able to see all the products related to MP3 when user searches MP3. | Fail | DEF_011 | Not started
21 | REQ_021 | TC_021 | Verify that whether user is able to see all the products related to iMac when user searches like iMac…..,website should ignore enteries like ….. Etc. | Fail | DEF_012 | Not started
22 | REQ_022 | TC_022 | Verify that whether user is able to see home page after entering in the website. | Pass | NA | NA
23 | REQ_023 | TC_023 | Verify that after clicking on each and every link on home page user should able to redirected towards a respective correct page. | In Progress | NA | In Progress
24 | REQ_024 | TC_024 | Verify that whether all the products displayed are available and no single product should be displayed more than once. | Fail | DEF_013 | In Progress
25 | REQ_025 | TC_025 | Verify that whether user is redirected to iPhone 12 pro max product after clicking on the link of iPhone 13 Max. | Fail | DEF_014 | In Progress
26 | REQ_026 | TC_026 | Verify that user is access the checklist without logged in or registerd. | Pass | NA | NA
27 | REQ_027 | TC_027 | Verify that user is access the checklist when logged in. | Pass | NA | NA
28 | REQ_028 | TC_028 | Verify that whether user is able to add product in Wishlist. | Pass | NA | NA
29 | REQ_029 | TC_029 | Verify that whether user is able to add product in Wishlist and after incresing quantity total price is also increasing. | Fail | DEF_015 | Not started
30 | REQ_030 | TC_030 | Verify that after add any product to a wishlist user should able to remove that product from the wishlist. | Pass | NA | NA
31 | REQ_031 | TC_031 | Verify that after adding any product to the wishlist the same product is added to wish list or not. | Pass | NA | NA
32 | REQ_032 | TC_032 | Verify that after adding any product to the wishlist user can able to add that product in cart or not. | Pass | NA | NA
33 | REQ_033 | TC_033 | Verify that Cart button is visible or not. | Pass | NA | NA
34 | REQ_034 | TC_034 | Verify that whether user is able to add any product to cart. | Pass | NA | NA
35 | REQ_035 | TC_035 | Verify that user is able to increase the quantity of the product in cart section. | Pass | NA | NA
36 | REQ_036 | TC_036 | Verify that after increasing the quantity of the product in the cart, total price is increasing or not. | Pass | NA | NA
37 | REQ_037 | TC_037 | Verify that user can able to add different different products to the cart section. | Pass | NA | NA
38 | REQ_038 | TC_038 | Verify that whether user is able to see all the taxes like VAT, that he has to pay while buying that particular product. | Pass | NA | NA
39 | REQ_039 | TC_039 | Verify that while checkout all the address details to deliver the product are fulfilled or not. | Pass | NA | NA
40 | REQ_040 | TC_040 | Verify that while confirming the order all the details are shown to the user or not. | Pass | NA | NA
41 | REQ_041 | TC_041 | Verify that whether user can do shopping bu category wise or not. | Pass | NA | NA
42 | REQ_042 | TC_042 | Verify that whether user is able to compare different different products. | Fail | DEF_016 | In Progress
43 | REQ_043 | TC_043 | Verify that Special Hot section is working or not and it is updated or not. | Fail | DEF_017 | In Progress
44 | REQ_044 | TC_044 | Verify that whether user is able to access the blog button or not. | Pass | NA | NA
45 | REQ_045 | TC_045 | Verify that whether user is able to comment on any particular blog or not. | Fail | DEF_018 | Not started
46 | REQ_046 | TC_046 | Verify that user is able to delete the comment that they have done. | Fail | DEF_019 | Not started
47 | REQ_047 | TC_047 | Verify that all the details entered are accurately stored or not. | Pass | NA | NA
48 | REQ_048 | TC_048 | Verify that user is able to Update password. | Fail | DEF_020 | In Progress
49 | REQ_049 | TC_049 | Verify that user is able to check order history or not. | Pass | NA | NA
50 | REQ_050 | TC_050 | Verify that user is able to access the download button or not. | Pass | NA | NA
51 | REQ_051 | TC_051 | Verify that user is able to do recurring payments and know about their recurring payments. | Pass | NA | NA
52 | REQ_052 | TC_052 | Verify that user can check the rewards points that they have got till now. | Pass | NA | NA
53 | REQ_053 | TC_053 | Verify that user can check the returns that they have made on the platform. | Pass | NA | NA
54 | REQ_054 | TC_054 | Verify that Your transaction button is functional or not. | Fail | DEF_021 | Not started
55 | REQ_055 | TC_055 | Verify that user can check whether they have Newsletter Subscription enabled or not. | Pass | NA | NA
56 | REQ_056 | TC_056 | Verify that user can update their Newsletter Subscription or not. | Pass | NA | NA
57 | REQ_057 | TC_057 | Verify that user can update their Newsletter Subscription or not. | Pass | NA | NA
58 | REQ_058 | TC_058 | Verify that Mega Menue button is Functional or not. | Fail | DEF_022 | In Progress
59 | REQ_059 | TC_059 | Verify that after clicking on Maga Menue, Special Hot, Blog, etc website is loading or not. | Fail | DEF_023 | In Progress
60 | REQ_060 | TC_060 | Verify that available quantity of product is displayed to the user if user wants to place order in bulk. | Fail | DEF_024 | In Progress
61 | REQ_061 | TC_061 | Verify that Addons Mudule is properly functional and easy to accessiable or not. | Fail | DEF_025 | In Progress
62 | REQ_062 | TC_062 | Verify that HP25 section is working or not. | Fail | DEF_026 | In Progress
63 | REQ_063 | TC_063 | Verrify that user is able to get that offer of HP25. | Fail | DEF_027 | In Progress
64 | REQ_064 | TC_064 | Verify that user is able to change the language to English. | Fail | DEF_028 | In Progress
65 | REQ_065 | TC_065 | Verify that all the content is in one language. | Fail | DEF_029 | In Progress
66 | REQ_066 | TC_066 | Verify that all the social media links of the website are available or not. | Fail | DEF_030 | In Progress
67 | REQ_067 | TC_067 | Verify that user is able to get Help from the website, if user want help. | Fail | DEF_031 | In Progress
68 | REQ_068 | TC_068 | Verify that filter button is available or not. | Fail | DEF_032 | In Progress
69 | REQ_069 | TC_069 | Verify that while logging out confirmation is taken from the user. | Fail | DEF_033 | In Progress
70 | REQ_070 | TC_070 | Verify that email and password properly matches. | Pass | NA | NA
71 | REQ_071 | TC_071 | Verify that About us section is filled with information or not. | Fail | DEF_034 | Not started
72 | REQ_072 | TC_072 | Verify that HTC touch pad image is properly shown or not. | Fail | DEF_035 | Not started
73 | REQ_073 | TC_073 | Verify that online payment option is functional or not. | Fail | DEF_036 | Not started
74 | REQ_074 | TC_074 | Verify that Easy return button is functional or not. | Fail | DEF_037 | Not started
75 | REQ_075 | TC_075 | Verify that 24/7 button is functional or not. | Fail | DEF_038 | Not started
76 | REQ_076 | TC_076 | Verify that Shop by category button is functional or not. | Pass | NA | NA
77 | REQ_077 | TC_077 | Verify that Shop by category button is functional and all the link are directed toward accurate pages. | Fail | DEF_039 | In Progress
78 | REQ_078 | TC_078 | Verify that user is able to remove warning of invalid comment. | Fail | DEF_040 | In Progress
79 | REQ_079 | TC_079 | Verify that companies name is displayed on the product or not. | Fail | DEF_041 | In Progress
80 | REQ_080 | TC_080 | Verify that product description is give properly or not. | Fail | DEF_042 | In Progress
81 | REQ_081 | TC_081 | Verify that FAQ section is available or not. | Pass | NA | NA
82 | REQ_082 | TC_082 | Verify that FAQ questions are proper and not repetative. | Fail | DEF_043 | In Progress
83 | REQ_083 | TC_083 | Verify that language of FAQ question and answer is same or not. | Fail | DEF_044 | In Progress
84 | REQ_084 | TC_084 | Verify that same thing is not displayed twice on the page. | Fail | DEF_045 | In Progress
85 | REQ_085 | TC_085 | Verify that while asking question wrong email ID is accepting or not. | Fail | DEF_046 | In Progress
86 | REQ_086 | TC_086 | Verify that product description is give properly or not. | Fail | DEF_047 | In Progress
87 | REQ_087 | TC_087 | Verify that description of the product is matching with the displayed product or not. | Fail | DEF_048 | In Progress
88 | REQ_088 | TC_088 | Verify that all the prices of the product are not fixed, user can see some decrement in the price of the product. | Fail | DEF_049 | In Progress
89 | REQ_089 | TC_089 | Verify that user is able to share the product if he want's to share the product. | Fail | DEF_050 | In Progress
90 | REQ_090 | TC_090 | Verify that if user is leaving website too early then user feedback is taken at that time. | Fail | DEF_051 | In Progress
91 | REQ_091 | TC_091 | Verify that search recommendation is working or not. | Fail | DEF_052 | In Progress
92 | REQ_092 | TC_092 | Verify that download from play store button is available and functional. | Fail | DEF_053 | In Progress
93 | REQ_093 | TC_093 | Verify that tracking order feature is functional or not. | Fail | DEF_054 | In Progress
94 | REQ_094 | TC_094 | Verify that video of product is being shown to user. | Fail | DEF_055 | In Progress
95 | REQ_095 | TC_095 | Verify that filter by colour, size, etc working properly. | Fail | DEF_056 | In Progress
96 | REQ_096 | TC_096 | Verify that user is unable to register with invalid email ID. | Fail | DEF_057 | In Progress
97 | REQ_097 | TC_097 | Verify that user is unable to register with invalid Telephone details. | Fail | DEF_058 | In Progress
98 | REQ_098 | TC_098 | Verify that companies website is https or not. | Pass | DEF_059 | In Progress
99 | REQ_099 | TC_099 | Verify that whether user is able to login using empty email Id and password. | Pass | DEF_060 | In Progress
100 | REQ_100 | TC_100 | Verify that user is unable to register with all invalid details. | Fail | DEF_061 | In Progress
101 | REQ_101 | TC_101 | Verify that color contrast is properly maintained. | Pass | NA | NA
102 | REQ_102 | TC_102 | Verify that font size is proper. | Pass | NA | NA
103 | REQ_103 | TC_103 | Verify that pinch-to-zoom workds properly. | Pass | NA | NA
104 | REQ_104 | TC_104 | Verify that features and functions works as expected. | Fail | DEF_063 | In Progress
105 | REQ_105 | TC_105 | Verify that user is unable to login with empty email ID and password field. | Pass | NA | NA
106 | REQ_106 | TC_106 | Verify that website should launch in less than 2 seconds. | Pass | NA | NA
107 | REQ_107 | TC_107 | Verify that all the links on home pages are getting launch in less than 2 seconds. | Pass | NA | NA
108 | REQ_108 | TC_108 | Verify that website performs under well low-speend broadband connection. | Pass | NA | NA
109 | REQ_109 | TC_109 | Verify that website launches quickly when cookies are not enabled. | Pass | NA | NA
110 | REQ_110 | TC_110 | Verify that under normal load website works well. | Pass | NA | NA
111 | REQ_111 | TC_111 | Verify that website performs well for continuous use for several hours. | Pass | NA | NA
112 | REQ_112 | TC_112 | Verify that after continuous use for several days website links loads in less than 2 sec. | Pass | NA | NA
113 | REQ_113 | TC_113 | Verify that Desktop's button is clickiable or not. | Pass | NA | NA
114 | REQ_114 | TC_114 | Verify that Laptop's button is clickiable or not. | Pass | NA | NA
115 | REQ_115 | TC_115 | Verify that Component button is clickiable or not. | Pass | NA | NA
116 | REQ_116 | TC_116 | Verify that Tablet button is clickiable or not. | Pass | NA | NA
117 | REQ_117 | TC_117 | Verify that Software button is clickiable or not. | Pass | NA | NA
118 | REQ_118 | TC_118 | Verify that Camera button is clickiable or not. | Pass | NA | NA
119 | REQ_119 | TC_119 | Verify that MP3 player button is clickiable or not. | Pass | NA | NA
120 | REQ_120 | TC_120 | Verify that Phones and PDA button is clickiable or not. | Pass | NA | NA
121 | REQ_121 | TC_121 | Verify that Component button is clickiable or not. | Pass | NA | NA
122 | REQ_122 | TC_122 | Verify that Mice and traceballs button is clickiable or not. | Pass | NA | NA
123 | REQ_123 | TC_123 | Verify that Fashion and accesssories button is clickiable or not. | Pass | NA | NA
124 | REQ_124 | TC_124 | Verify that beauty button is clickiable or not. | Pass | NA | NA
125 | REQ_125 | TC_125 | Verify that Saloon button is clickiable or not. | Pass | NA | NA
126 | REQ_126 | TC_126 | Verify that Fashion and accesssories button is clickiable or not. | Pass | NA | NA
127 | REQ_127 | TC_127 | Verify that Autoparts and accessories button is clickiable or not. | Pass | NA | NA
128 | REQ_128 | TC_128 | Verify that Washing machine button is clickiable or not. | Pass | NA | NA
129 | REQ_129 | TC_129 | Verify that Printers and scanners button is clickiable or not. | Pass | NA | NA