## Sheet1
Summary of Test Execution
Total Test Cases | Executed Test Cases | Passed Test Cases | Failed Test Cases | Blocked Test Cases
129 | 129 | 70 | 59 | 0
Detailed Test Execution Results
Module | Requirement | Test Case ID | Test Case Description | Status | Priority | Defect ID
Registration |  | TS_001 | Verify that user is unable to register with invalid email ID. | Fail | High | Bug_001
|  | TS_002 | Verify that user is unable to register with invalid name. | Fail | Medium | Bug_002
|  | TS_003 | Verify that user is unable to register with invalid First name. | Fail | Low | Bug_003
|  | TS_004 | Verify that user is unable to register with invalid Telephone details. | Fail | High | Bug_004
|  | TS_005 | Verify that user is unable to register with valid details. | Pass
|  | TS_006 | Verify that user is unable to register with all invalid details. | Fail | High | Bug_005
|  | TS_007 | Verify that whether user is able to login using valid email Id and password. | Pass
Login |  | TS_008 | Verify that whether user is able to login using invalid email Id and valid password. | Pass
|  | TS_009 | Verify that whether user is able to login using valid email Id and invalid password. | Pass
|  | TS_010 | Verify that whether user is able to login using invalid email Id and invalid password. | Pass
|  | TS_011 | Verify that whether user is able to login using empty email Id and password. | Pass
|  | TS_012 | Verify that whether user is able to login using empty email ID field. | Pass
|  | TS_013 | Verify that whether user is able to login using empty password field. | Pass
|  | TS_014 | Verify that whether user is able to see search bar on the home page. | Pass
Search |  | TS_015 | Verify that whether user is unable to click the search option without entering any thing in search bar field. | Fail | Low | Bug_006
|  | TS_016 | Verify that whether user is able to see all the products related to iphone only,when user enters I phone in search bar. | Fail | Low | Bug_007
|  | TS_017 | Verify that user is unable to see any kind of search results unless and untill user provides any search. And user should get pop up message like please enter in ssearch field. | Fail | Low | Bug_008
|  | TS_018 | Verify that whether user is able to see iMac product, but not that product should not be repetative. | Fail | Low | Bug_009
|  | TS_019 | verify that whether user is able to see all the products related to iMac when user searches iMacc in search bar. | Fail | High | Bug_010
|  | TS_020 | Verify that whether user is able to see all the products related to MP3 when user searches MP3. | Fail | High | Bug_011
|  | TS_021 | Verify that whether user is able to see all the products related to iMac when user searches like iMac…..,website should ignore enteries like ….. Etc. | Fail | High | Bug_012
|  | TS_022 | Verify that whether user is able to see home page after entering in the website. | Pass
Home |  | TS_023 | Verify that after clicking on each and every link on home page user should able to redirected towards a respective correct page. | Inprogress | High
|  | TS_024 | Verify that whether all the products displayed are available and no single product should be displayed more than once. | Fail | Low | Bug_013
|  | TS_025 | Verify that whether user is redirected to iPhone 12 pro max product after clicking on the link of iPhone 13 Max. | Fail | High | Bug_014
|  | TS_026 | Verify that user is access the checklist without logged in or registerd. | Pass
Checklist |  | TS_027 | Verify that user is access the checklist when logged in. | Pass
|  | TS_028 | Verify that whether user is able to add product in Wishlist. | Pass
|  | TS_029 | Verify that whether user is able to add product in Wishlist and after incresing quantity total price is also increasing. | Fail | High | Bug_015
|  | TS_030 | Verify that after add any product to a wishlist user should able to remove that product from the wishlist. | Pass
|  | TS_031 | Verify that after adding any product to the wishlist the same product is added to wish list or not. | Pass
|  | TS_032 | Verify that after adding any product to the wishlist user can able to add that product in cart or not. | Pass
|  | TS_033 | Verify that Cart button is visible or not. | Pass
Cart |  | TS_034 | Verify that whether user is able to add any product to cart. | Pass
|  | TS_035 | Verify that user is able to increase the quantity of the product in cart section. | Pass
|  | TS_036 | Verify that after increasing the quantity of the product in the cart, total price is increasing or not. | Pass
|  | TS_037 | Verify that user can able to add different different products to the cart section. | Pass
|  | TS_038 | Verify that whether user is able to see all the taxes like VAT, that he has to pay while buying that particular product. | Pass
Checkout |  | TS_039 | Verify that while checkout all the address details to deliver the product are fulfilled or not. | Pass
|  | TS_040 | Verify that while confirming the order all the details are shown to the user or not. | Pass
|  | TS_041 | Verify that whether user can do shopping bu category wise or not. | Pass
Category wise |  | TS_042 | Verify that whether user is able to compare different different products. | Fail | Low | Bug_016
Compare |  | TS_043 | Verify that Special Hot section is working or not and it is updated or not. | Fail | Medium | Bug_017
Special hot |  | TS_044 | Verify that whether user is able to access the blog button or not. | Pass
Blog |  | TS_045 | Verify that whether user is able to comment on any particular blog or not. | Fail | Low | Bug_018
|  | TS_046 | Verify that user is able to delete the comment that they have done. | Fail | Medium | Bug_019
|  | TS_047 | Verify that all the details entered are accurately stored or not. | Pass
Update password |  | TS_048 | Verify that user is able to Update password. | Fail | High
Order history |  | TS_049 | Verify that user is able to check order history or not. | Pass
Downloads |  | TS_050 | Verify that user is able to access the download button or not. | Pass
Recurring payments |  | TS_051 | Verify that user is able to do recurring payments and know about their recurring payments. | Pass
Rewards points |  | TS_052 | Verify that user can check the rewards points that they have got till now. | Pass
Return |  | TS_053 | Verify that user can check the returns that they have made on the platform. | Pass
Transition |  | TS_054 | Verify that Your transaction button is functional or not. | Fail | High | Bug_020
Newsletter |  | TS_055 | Verify that user can check whether they have Newsletter Subscription enabled or not. | Pass
|  | TS_056 | Verify that user can update their Newsletter Subscription or not. | Pass
|  | TS_057 | Verify that user can update their Newsletter Subscription or not. | Pass
Mega menu |  | TS_058 | Verify that Mega Menue button is Functional or not. | Fail | High | Bug_021
|  | TS_059 | Verify that after clicking on Maga Menue, Special Hot, Blog, etc website is loading or not. | Fail | High | Bug_022
Availability |  | TS_060 | Verify that available quantity of product is displayed to the user if user wants to place order in bulk. | Fail | Medium | Bug_023
Addon module |  | TS_061 | Verify that Addons Mudule is properly functional and easy to accessiable or not. | Fail | Low | Bug_024
HP25 |  | TS_062 | Verify that HP25 section is working or not. | Fail | Low | Bug_025
HP25 |  | TS_063 | Verrify that user is able to get that offer of HP25. | Fail | High | Bug_026
Language |  | TS_064 | Verify that user is able to change the language to English. | Fail | High | Bug_027
Language |  | TS_065 | Verify that all the content is in one language. | Fail | High | Bug_028
Social media |  | TS_066 | Verify that all the social media links of the website are available or not. | Fail | High | Bug_029
Help |  | TS_067 | Verify that user is able to get Help from the website, if user want help. | Fail | High | Bug_030
Filter button |  | TS_068 | Verify that filter button is available or not. | Fail | Low | Bug_031
Log out |  | TS_069 | Verify that while logging out confirmation is taken from the user. | Fail | Low | Bug_032
Email and password |  | TS_070 | Verify that email and password properly matches. | Pass
About section |  | TS_071 | Verify that About us section is filled with information or not. | Fail | Medium | Bug_033
HTC Touch pad |  | TS_072 | Verify that HTC touch pad image is properly shown or not. | Fail | Low | Bug_034
Online payment |  | TS_073 | Verify that online payment option is functional or not. | Fail | High | Bug_035
Easy return |  | TS_074 | Verify that Easy return button is functional or not. | Fail | Medium | Bug_036
24/7 support |  | TS_075 | Verify that 24/7 button is functional or not. | Fail | High | Bug_037
|  | TS_076 | Verify that Shop by category button is functional or not. | Pass
Shop by category |  | TS_077 | Verify that Shop by category button is functional and all the link are directed toward accurate pages. | Fail | Medium | Bug_038
Invalid comment |  | TS_078 | Verify that user is able to remove warning of invalid comment. | Fail | Low | Bug_039
Company name |  | TS_079 | Verify that companies name is displayed on the product or not. | Fail | Low | Bug_040
Product D |  | TS_080 | Verify that product description is give properly or not. | Fail | Low | Bug_041
FAQ |  | TS_081 | Verify that FAQ section is available or not. | Pass
|  | TS_082 | Verify that FAQ questions are proper and not repetative. | Fail | Low | Bug_042
|  | TS_083 | Verify that language of FAQ question and answer is same or not. | Fail | High | Bug_043
|  | TS_084 | Verify that same thing is not displayed twice on the page. | Fail | Low | Bug_044
Ask question |  | TS_085 | Verify that while asking question wrong email ID is accepting or not. | Fail | Medium | Bug_045
Product description |  | TS_086 | Verify that product description is give properly or not. | Fail | Medium | Bug_046
|  | TS_087 | Verify that description of the product is matching with the displayed product or not. | Fail | High | Bug_047
Price |  | TS_088 | Verify that all the prices of the product are not fixed, user can see some decrement in the price of the product. | Fail | Medium | Bug_048
Share product |  | TS_089 | Verify that user is able to share the product if he want's to share the product. | Fail | Low | Bug_049
Leave the site |  | TS_090 | Verify that if user is leaving website too early then user feedback is taken at that time. | Fail | Low | Bug_050
Search recommendation |  | TS_091 | Verify that search recommendation is working or not. | Fail | Low | Bug_051
Download from play store |  | TS_092 | Verify that download from play store button is available and functional. | Fail | Low | Bug_052
Track your order |  | TS_093 | Verify that tracking order feature is functional or not. | Fail | High | Bug_053
Video of the product |  | TS_094 | Verify that video of product is being shown to user. | Fail | Low | Bug_054
Color and size |  | TS_095 | Verify that filter by colour, size, etc working properly. | Fail | Low | Bug_055
|  | TS_096 | Verify that user is unable to register with invalid email ID. | Fail | High | Bug_056
Register |  | TS_097 | Verify that user is unable to register with invalid Telephone details. | Fail | High | Bug_057
Website url |  | TS_098 | Verify that companies website is https or not. | Pass
Login |  | TS_099 | Verify that whether user is able to login using empty email Id and password. | Pass
Register |  | TS_100 | Verify that user is unable to register with all invalid details. | Fail | High | Bug_058
Color |  | TS_101 | Verify that color contrast is properly maintained. | Pass
Font size |  | TS_102 | Verify that font size is proper. | Pass
Overall Features |  | TS_103 | Verify that pinch-to-zoom workds properly. | Pass
Login |  | TS_104 | Verify that features and functions works as expected. | Fail | High | Bug_059
Website launch |  | TS_105 | Verify that user is unable to login with empty email ID and password field. | Pass
Home |  | TS_106 | Verify that website should launch in less than 2 seconds. | Pass
|  | TS_107 | Verify that all the links on home pages are getting launch in less than 2 seconds. | Pass
Website performance |  | TS_108 | Verify that website performs under well low-speend broadband connection. | Pass
|  | TS_109 | Verify that website launches quickly when cookies are not enabled. | Pass
|  | TS_110 | Verify that under normal load website works well. | Pass
|  | TS_111 | Verify that website performs well for continuous use for several hours. | Pass
|  | TS_112 | Verify that after continuous use for several days website links loads in less than 2 sec. | Pass
Desktop |  | TS_113 | Verify that Desktop's button is clickiable or not. | Pass
Laptop |  | TS_114 | Verify that Laptop's button is clickiable or not. | Pass
Component |  | TS_115 | Verify that Component button is clickiable or not. | Pass
Tablet |  | TS_116 | Verify that Tablet button is clickiable or not. | Pass
Software |  | TS_117 | Verify that Software button is clickiable or not. | Pass
Camera |  | TS_118 | Verify that Camera button is clickiable or not. | Pass
MP3 player |  | TS_119 | Verify that MP3 player button is clickiable or not. | Pass
Phones and PDA |  | TS_120 | Verify that Phones and PDA button is clickiable or not. | Pass
Components |  | TS_121 | Verify that Component button is clickiable or not. | Pass
Mice and traceballs |  | TS_122 | Verify that Mice and traceballs button is clickiable or not. | Pass
Fashion and accessories |  | TS_123 | Verify that Fashion and accesssories button is clickiable or not. | Pass
Beauty |  | TS_124 | Verify that beauty button is clickiable or not. | Pass
Saloon |  | TS_125 | Verify that Saloon button is clickiable or not. | Pass
Fashion and accessories |  | TS_126 | Verify that Fashion and accesssories button is clickiable or not. | Pass
Autoparts and accessories |  | TS_127 | Verify that Autoparts and accessories button is clickiable or not. | Pass
Washing machine |  | TS_128 | Verify that Washing machine button is clickiable or not. | Pass
Printers and scanners |  | TS_129 | Verify that Printers and scanners button is clickiable or not. | Pass